## Instructions
Case Study Project Tracker
Java Full Stack Training — Capstone Case Study
How to use this workbook
1. Go to the 'Task Tracker' sheet. Each trainee/team lists the tasks (modules, features, sub-tasks) for their case study there — similar to a sprint backlog in a real software team.
2. Update your task's Status, % Complete, and Hours Spent regularly (daily/every alternate day) — do not wait until the deadline.
3. Use the 'Daily Work Log' sheet every working day to record what you did, like a standup update: Yesterday's work, Today's plan, and any blockers.
4. The 'Dashboard' sheet updates automatically from the Task Tracker sheet — do not edit it directly.
5. Cells shaded light yellow are example rows — replace them with your own data. Do not delete the header rows.
Column & Status Legend (Task Tracker sheet)
Status values: Not Started, In Progress, Blocked, In Review, Completed
Priority values: High, Medium, Low
% Complete: enter a whole number between 0 and 100 (e.g., 50 for 50%).
Hours Estimated / Hours Spent: enter numeric hours (e.g., 4, 6.5).
Remarks / Blockers: mention any dependency, doubt, or issue blocking progress — leave blank if none.
Column Legend (Daily Work Log sheet)
Fill one row per person per working day. Task ID should match the Task Tracker sheet where applicable.
Conventions used in this workbook
Yellow fill = example row / cells you should edit or replace with your own data.
White/grey rows = your data entry rows (add as many as needed).
Dashboard values and charts = auto-calculated, formula-driven — do not overwrite.

## Task Tracker
Case Study Task Tracker
Updated vehicle-registration project tracker for 02–05 October 2026. Task fields follow the Case Study Project Tracker format.
Task ID | Module / Feature | Task Description | Assigned To | Priority | Status | Start Date | Due Date | Est. Hours | Hours Spent | % Complete | Remarks / Blockers | Last Updated
T-001 | Backend Entities & Repositories | Implemented JPA entities for the vehicle-registration domain and repositories for database persistence and lookup queries. | Sadhna Gupta | High | Completed | 2026-10-02 | 2026-10-05 | 16 | 16 | 100 | Completed as part of the backend implementation; existing database structure used. | 2026-10-05
T-002 | Backend Controllers & Validation | Implemented REST controllers, request validation and CORS for vehicle, registration certificate, application, administration, authentication, payment and fee-rule operations. | Sadhna Gupta & Dharmendra | High | Completed | 2026-10-02 | 2026-10-05 | 10 | 10 | 100 | Controllers completed and integrated with the service layer. | 2026-10-05
T-003 | Backend Exceptions & Error Handling | Implemented business exceptions, API error handling and global exception responses for registration, payment, owner, employee and request-validation scenarios. | Sadhna Gupta & Dharmendra | High | Completed | 2026-10-02 | 2026-10-05 | 8 | 8 | 100 | Exception handling completed for the project workflow. | 2026-10-05
T-004 | Request & Response DTOs | Implemented request and response DTOs for owner, employee, application, vehicle, payment, fee-rule, audit and registration-certificate data. | Dharmendra & Yogesh | High | Completed | 2026-10-02 | 2026-10-05 | 10 | 10 | 100 | DTO layer completed and aligned with controller/service data flow. | 2026-10-05
T-005 | Backend Enums & Utilities | Implemented backend enums for account, application, fuel, identity proof, inspection, payment, employee and vehicle workflow values, plus password utility support. | Dharmendra | Medium | Completed | 2026-10-02 | 2026-10-05 | 6 | 6 | 100 | Enums and password utility completed. | 2026-10-05
T-006 | Backend Service Interfaces | Implemented service contracts for authentication, employee management, audit, registration submission, application review/query, payments, fee rules and reporting. | Sadhna Gupta & Dharmendra | High | Completed | 2026-10-02 | 2026-10-05 | 8 | 8 | 100 | Service interfaces completed for the project modules. | 2026-10-05
T-007 | Backend Service Implementations | Implemented business logic for registration submission, reference tracking, corrections, payment, verification, inspection, RC generation, fees, reports, authentication, employee and account management. | Sadhna Gupta & Dharmendra | High | Completed | 2026-10-02 | 2026-10-05 | 16 | 16 | 100 | Service implementations completed and tested with the application workflow. | 2026-10-05
T-008 | Frontend Application & API Integration | Implemented React application entry/navigation, API client, Bootstrap/CSS integration, development setup and registration-data loading. | Sadhna Gupta & Dharmendra & Yogesh | High | Completed | 2026-10-02 | 2026-10-05 | 10 | 10 | 100 | Frontend application and API integration completed. | 2026-10-05
T-009 | Frontend Registration & Authentication Components | Implemented owner registration/login, employee login, owner forms, vehicle form, new registration, applications, vehicles and related frontend screens. | Sadhna Gupta & Dharmendra | High | Completed | 2026-10-02 | 2026-10-05 | 12 | 12 | 100 | Core frontend components completed for registration and authentication flows. | 2026-10-05
T-010 | Frontend Administration & Fee Components | Implemented employee/account administration screen and registration fee display components. | Yogesh | Medium | Completed | 2026-10-03 | 2026-10-05 | 4 | 4 | 100 | Administration and fee display components completed. | 2026-10-05
T-011 | Application Status & Workflow Display | Implemented application status badges and workflow progress steps for frontend display. | Durga Prasad | Medium | Completed | 2026-10-05 | 2026-10-05 | 3 | 3 | 100 | Small frontend workflow-display work completed. | 2026-10-05
T-012 | Backend Setup & Testing | Configured Spring Boot application startup, MySQL/JPA settings and Maven dependencies; completed 17 passing JUnit API tests covering validation and new-registration RC generation. | Sadhna Gupta | High | Completed | 2026-10-04 | 2026-10-05 | 8 | 8 | 100 | Backend setup and API tests completed successfully. | 2026-10-05

## Daily Work Log
Daily Work Log
Fill one row per person per working day — like a daily standup update.
Date | Participant Name | Task ID | Work Done Today | Hours Spent | Status | Blockers / Issues | Plan for Tomorrow
2026-10-02 | Sadhna Gupta & Dharmendra | T-001/T-002/T-003 | Worked on backend entities, repositories, controllers, validation and exception handling for the vehicle-registration workflow. | 8 | completed | None | Continue DTOs and service interfaces.
2026-10-03 | Dharmendra & Yogesh | T-004/T-005/T-006 | Completed request/response DTOs, backend enums, utilities and service interfaces; continued frontend setup and components. | 8 | completed | None | Continue service implementations and frontend integration.
2026-10-04 | Sadhna Gupta & Dharmendra & Yogesh | T-007/T-008/T-009/T-010 | Completed backend service implementations and major React application, API, registration, authentication, administration and fee components. | 8 | completed | None | Finish workflow display, setup and testing.
2026-10-05 | Sadhna Gupta & Dharmendra & Yogesh & Durga Prasad | T-011/T-012 | Completed frontend status/progress display, backend setup and 17 passing JUnit API tests covering validation and new-registration RC generation. | 8 | completed | None | Project work for the tracker period completed.

## Dashboard
Project Tracker Dashboard
Auto-calculated from the 'Task Tracker' sheet — do not edit these cells.
Task Status Summary
Total Tasks
Not Started
In Progress
Blocked
In Review
Completed
Effort Summary
Total Est. Hours
Total Hours Spent
Avg. % Complete
Status | Count | Metric | Hours
Not Started |  | Est. Hours
In Progress |  | Spent Hours
Blocked
In Review
Completed